## schedule
ID | WBS | Task | Responsible | Accountable | Consulted | Informed | Duration (Days) | Progress | Start Date | End Date
| 1 | Project Planning & Architecture |  |  |  |  | 13 |  | 2026-10-11 | 2026-10-23
1 | 1.1 | Define business objective | Zuzanna, Martyna, Hania | Hania | Janusz Rafałko Ph.D. | --- | 3 | 100% | 2026-10-11 | 2026-10-13
2 | 1.2 | Define system vision | Zuzanna, Martyna, Hania | Hania | --- | Janusz Rafałko Ph.D. | 3 | 100% | 2026-10-11 | 2026-10-13
3 | 1.3 | Define functional requirements | Hania, Martyna | Hania | Zuzanna | Janusz Rafałko Ph.D. | 4 | 100% | 2026-10-13 | 2026-10-16
4 | 1.4 | Define non-functional requirements | Zuzanna | Zuzanna | Hania, Martyna | Janusz Rafałko Ph.D. | 3 | 100% | 2026-10-14 | 2026-10-16
5 | 1.5 | Perform risk analysis | Martyna, Zuzanna | Zuzanna | Hania | Janusz Rafałko Ph.D. | 2 | 100% | 2026-10-14 | 2026-10-15
6 | 1.6 | Prepare project schedule and divide tasks between team members | Zuzanna, Hania | Zuzanna | Martyna | --- | 4 | 100% | 2026-10-16 | 2026-10-19
7 | 1.7 | Decide on the formats in which data will be stored and handled | Martyna, Hania | Martyna | Zuzanna | --- | 1 | 100% | 2026-10-16 | 2026-10-16
8 | 1.8 | Define system architecture and main classes | Martyna, Hania, Zuzanna | Martyna | --- | --- | 5 | 0% | 2026-10-19 | 2026-10-23
9 | 1.9 | Decide on main dependencies (e.g. external libraries) | Martyna | Martyna | Hania, Zuzanna | --- | 8 | 70% | 2026-10-13 | 2026-10-20
10 | 1.10 | Prepare a shortlist of algorithms to be implemented for each module | Martyna, Hania, Zuzanna | Martyna | Janusz Rafałko Ph.D. | --- | 11 | 50% | 2026-10-13 | 2026-10-23
| 2 | Module 1: Document Fragmentation |  |  |  |  | 13 |  | 2026-10-19 | 2026-10-31
11 | 2.1 | Implement input handling | Zuzanna | Zuzanna | Hania, Martyna | --- | 2 | 0% | 2026-10-19 | 2026-10-20
12 | 2.2 | Implement fragmentation algorithms | Zuzanna, Martyna, Hania | Hania | --- | --- | 10 | 0% | 2026-10-19 | 2026-10-28
13 | 2.3 | Implement the random rotation of each fragment | Martyna | Martyna | Zuzanna, Hania | --- | 3 | 0% | 2026-10-21 | 2026-10-23
14 | 2.4 | Implement fragment placement on background | Hania | Hania | Martyna, Zuzanna | --- | 3 | 0% | 2026-10-21 | 2026-10-23
15 | 2.5 | Implement image export | Zuzanna | Zuzanna | Hania, Martyna | --- | 2 | 0% | 2026-10-23 | 2026-10-24
16 | 2.6 | Write unit tests for module 1 | Martyna | Martyna | Zuzanna, Hania | --- | 3 | 0% | 2026-10-26 | 2026-10-28
17 | 2.7 | Validate results through subjective observation | Hania | Hania | Martyna, Zuzanna | Janusz Rafałko Ph.D. | 9 | 0% | 2026-10-23 | 2026-10-31
| 3 | Module 2A: Fragment Extraction |  |  |  |  | 7 |  | 2026-11-01 | 2026-11-07
18 | 3.1 | Implement the algorithm for finding fragment borders | Hania | Hania | Martyna, Zuzanna | --- | 4 | 0% | 2026-11-01 | 2026-11-04
19 | 3.2 | Implement extracting the fragments into separate objects | Martyna | Martyna | Zuzanna, Hania | --- | 2 | 0% | 2026-11-04 | 2026-11-05
20 | 3.3 | Write unit tests for module 2A | Zuzanna | Zuzanna | Hania, Martyna | --- | 2 | 0% | 2026-11-06 | 2026-11-07
| 4 | Module 2B: Document Reconstruction |  |  |  |  | 17 |  | 2026-11-08 | 2026-11-24
21 | 4.1 | Implement shape-based reconstruction algorithms | Zuzanna, Martyna, Hania | Hania | --- | Janusz Rafałko Ph.D. | 13 | 0% | 2026-11-08 | 2026-11-20
22 | 4.2 | Implement content-based reconstruction algorithms | Zuzanna, Martyna, Hania | Martyna | --- | Janusz Rafałko Ph.D. | 13 | 0% | 2026-11-08 | 2026-11-20
23 | 4.3 | Write unite tests for module 2B | Zuzanna | Zuzanna | Hania, Martyna | --- | 4 | 0% | 2026-11-21 | 2026-11-24
| 5 | Benchmarking |  |  |  |  | 6 |  | 2026-11-25 | 2026-11-30
24 | 5.1 | Implement the extraction of text from a reconstructed document | Zuzanna | Zuzanna | Hania, Martyna | --- | 3 | 0% | 2026-11-25 | 2026-11-27
25 | 5.2 | Prepare benchmarking scenarios for various input types | Hania | Hania | Martyna, Zuzanna | --- | 3 | 0% | 2026-11-25 | 2026-11-27
26 | 5.3 | Perform automated benchmarking of reconstruction algorithms using automated text extraction | Martyna | Martyna | Zuzanna, Hania | --- | 3 | 0% | 2026-11-27 | 2026-11-29
27 | 5.4 | Perform manual benchmarking of reconstruction algorithms based on final document readability | Zuzanna, Martyna, Hania | Zuzanna | --- | --- | 4 | 0% | 2026-11-26 | 2026-11-29
28 | 5.5 | Construct heuristics for algorithm selection | Hania | Hania | Martyna, Zuzanna | Janusz Rafałko Ph.D. | 2 | 0% | 2026-11-29 | 2026-11-30
| 6 | Integration, UI, |  |  |  |  | 34 |  | 2026-11-01 | 2026-12-04
29 | 6.1 | Integrate modules into an unified pipeline | Zuzanna | Zuzanna | Hania, Martyna | Janusz Rafałko Ph.D. | 4 | 0% | 2026-12-01 | 2026-12-04
30 | 6.2 | Building UI | Zuzanna, Martyna, Hania | Martyna | Zuzanna, Hania | Janusz Rafałko Ph.D. | 30 | 0% | 2026-11-01 | 2026-11-30
| 7 | Documentation & Thesis writing |  |  |  |  | 62 |  | 2026-12-01 | 2027-01-31
31 | 7.1 | Compile existing documentation and benchmarking results into initial thesis draft | Zuzanna, Martyna, Hania | Zuzanna | --- | --- | 20 | 0% | 2026-12-01 | 2026-12-20
32 | 7.2 | Write core chapters for thesis | Zuzanna, Martyna, Hania | Hania | Janusz Rafałko Ph.D. | --- | 38 | 0% | 2026-12-01 | 2027-01-07
33 | 7.3 | Final buffer time, thesis polishing and defense presentation | Zuzanna, Martyna, Hania | Martyna | --- | Janusz Rafałko Ph.D. | 25 | 0% | 2027-01-07 | 2027-01-31
Formulas:
Start Date = MIN([Start Date, row below]:J11)
End Date = MAX([End Date, row below]:K11)